CYCLADES - IST –2000-25456

An Open Collaborative Virtual Archive Environment

###### Annual Report

1 February  2001– 31 January 2002

Editor :Remi Ronchaud– ERCIM

2004, route des Lucioles

B.P. 93

06902 Sophia Antipolis

France

Bruno.le_dantec@ercim.org

Remi.ronchaud@ercim.org

Annual Report 1

Covered period: From 1 February 2001 to 31 January 2002

Project  Scientific Manager

Name: Umberto Straccia

Address: Istituto di Elaborazione dell'Informazione

Consiglio Nazionale delle Ricerche     Via Moruzzi,1 , 56124, Pisa (Italy)

Phone: 39. 050 315 2894        Fax:  39. 050 315 2810

e-mail: straccia@iei.pi.cnr.it

Management report editor

Name: Remi Ronchaud

Address : 2004 Route des Lucioles - BP 93 - 06902 Sophia Antipolis cedex - France

Phone: 33 4 92 38 50 12	Fax : 33 4 92 38 50 11

e-mail: remi.ronchaud@ercim.org

# 1.    EXECUTIVE SUMMARY

We report on the initial year of the Cyclades project. The work accomplished and the accompanying activities concerning this project during this period are reported.

We report on the scientific progress of the ideas started out in this project and pursued by the partners. The initial work has used the project web pages to display and communicate the ideas exchanged which led to the first reports. Management activities are reported concerning the dissemination activities pursued by the partners.

# 1.1 Project structure

Project organisation and synergy have been initiated through several meetings attended by all partners.  All advances of the projects and results are recorded in the common project web pages, http://www.ercim.org/cyclades, which contains all reports, working documents and deliverables as well as any useful information. Such a system facilitates communication between partners, each of them being aware at any time of the state of the project.

The project structure is very well documented in the project programme. Both the scientific and management structures of the project are described in every detail as required

# 1.2 Scientific Progress

While the first six months of the project were focusing on :

- specifying the end users requirements : needs, expectations and ,

- Designing the Global system Architecture,

- Defining a Preliminary exploitation Plan,

- And Coordinating Cyclades with the Open Archive Initiative,

the main goal of the second six months of the project was to work on WP3, System Development. In particular the objective was both to start with the implementation of the various CYCLADES services, as well as to work on the definition of the various algorithms and database schema involved.

It is also essential to mention that substantial work has been dedicated to the metadata record indexing algorithm in the Access Service, to the filtering algorithms and to the recommendation algorithms in the Filtering and Recommendation Service. The detailed specification of the Services will be part of Deliverable 3.0.1, which will be ready at the beginning of February. A draft version is currently available on the web site.

These interdependent tasks which are now achieved, enable the project to move forward and towards the effective implementation phase. A lot of concertation within the consortium was necessary to provide choices compatible with the end users interest, the technical constraints and  the system potentialities.

# 1.3 Results

Through out this first year, the Cyclades project has been producing the following deliverables:

- D1.1 User Requirements Report

- D2.2.1 Global System Architecture Report

- D7.1.1 Web Site

- D7.2.1 Dissemination and Use Plan

- D8.1.1a Co-ordination Report and Preliminary Version

- D9.1.1 Quality Assurance Plan

- D9.2.1Progress Report 1

- D8.1.1Coordination Report (Final version)

- D9.2.1 Progress report 2

- D 9.1.2Annual Report

Cyclades has also achieved the following tasks necessary to the full project completion:

- collect and analyse end users requirements;

- define and prepare the functional and architectural specifications of Cyclades

- ensure close cooperation with the Open Archive Initiative

- disseminate information about the project;

- manage both scientifically and administratively the project.

A particular effort was spent in carefully specifying an essential deliverable, the system architecture (D2.2.1), in order to provide the implementation and integration work with reliable information.

# 2.    MANAGEMENT

There have been various activities at both the consortium and local level of each institute.

2.1 Meetings

The project management has organised the kick-off meeting which took place in Pisa, Italy on 19 February 2001. The meeting was very constructive and well organised from the point of view of work achieved. The emphasis was on defining precisely all the tasks assigned with a particular attention on the  definition of the end user requirements that stand for the basis on which all the work will afterwards rely.

At the same time, partners involved in the system design and in the collaboration with the Open Archive Initiative were also given short and early deadlines to give the project a certain reactivity. The agenda of the Kick Off Meeting is  to be found hereafter:

During this meeting, the partners had their first opportunity to investigate precisely the complementarity of their respective tasks and exchange ideas with each other about the system design and about Cyclades’s cooperation with OAI.

Discussions also took place and every effort was made from all partners to inform the rest about their work, experience and expectations within this project.

All the presentations are available for downloading from the dedicated web pages (using Member / Cyclades) at http://www.ercim.org/cyclades/vip/.

Regular meetings, sometimes informal, were held to maintain a general cohesion within the project. From 7th to the 11th  of May 2001, a Technical Meeting took place in Crete. The core of the discussion was to determine more precisely the System Functional Specifications. This meeting proved very useful since a general agreement was found among partners and the general motivation of the Cyclades team was boosted.

Official Plenary Meetings are also organised when necessary to address very specific issues. The one held in the Fraunhofer (ex-GMD) institute in Bonn on the 29 and 30 of November 2001 was organised to address:

1.  the current implementation state

2.  discuss the organisation of review in January

3.  the preparation of Deliverable D3.0.1 due to early February.

The minutes of all meetings are  found on the web site along with the conclusions and a list of the next actions and priorities to be carried out during the next months.

# 2.2 Web Server

The official Web server was set up at the ERCIM address.

http://www.ercim.org/cyclades,

This web site has been created to dispatch various information related to the project. It includes a  restricted area for the Consortium, mainly used as document repository, and a public section. The site was opened for public access in January 2001 and is regularly updated.

Particular effort was made by the management to provide the consortium with the best work environment possible. On top of this regularly updated web site, all the partners has also access to the BSCW workspace. The BSCW (Basic Support for Cooperative Work) enables collaboration over the Web. BSCW is a 'shared workspace' system which supports document uploading, event notification, group management and much more.

This has proven extremely useful when it came to exchange ideas, representations of the system architecture or any other document and deliverable in progress. The final version of these documents is put on the regular web page as the BSCW is a mere workspace.

All additional information is to be found in D 7.1.1 that was produced.

# 2.3 Presentations in Conferences and Exhibitions and Public Relations

Partners were made very aware of the importance for the project to be represented in various public events. In this perspective the management has been informing all the partners about upcoming conferences, workshops or meetings related to the field of Digital Libraries. Below are some of the events in which Cyclades was represented:

- ERCIM’s and CNR’s contacts with the DELOS Network of Excellence were a real support in bringing Cyclades to take part to major DL events.

- EU-DL All Projects meeting, Luxemburg, February 2001

- DELOS, IPI RAS and IITE Workshop on European/Russian Cooperation in Digital Libraries, Moscow, June 2001

- ECIR, Darmstadt, April 2001

- Participation in a panel on ‘e-Democracy held on the 25 and 26 June 2001: A Panacea or Pandora’s Box?’ at the 14th Bled Electronic Commerce Conference ‘e-Everything: e-Commerce, e-Government, e-Household, e-Democracy’.

- OAI Open Meeting, Germany, 26 February 2001

These meetings and conference provided the opportunity for a representative of Cyclades to discuss and promote the project in the context of DL research and virtual communities.

Effort was also made by the management to tighten the links between Cyclades and DELOS. Indeed the aim of the DELOS Network of Excellence for Digital Libraries (DLs) is to provide an open context in which an international research agenda for future research activities in the digital libraries  domain can be developed.

This Network constitutes a reference point for all DL projects funded by the 5th Framework Programme, stimulating the exchange of experiences and know-how in this multidisciplinary domain, and will also establish close contacts with relevant application communities.

Therefore it appeared as a necessity for the management to integrate Cyclades into this framework DELOS provides.

Additionally, the Cyclades fact sheet organised as a leaflet are regularly distributed to various meetings and Conferences to enhance Cyclades visibility. For example, during the IST Conference held in Dusseldorf  on the 3,4 and 5 December 2001,  ERCIM has distributed several copies of this fact sheet, not only to representatives of the European Commission but also to NSF delegates and several  heads of research Institutes in Europe.

In addition,  ERCIM has distributed a pack of these fact sheets to every single one of its fifteen European members institutes in distributed across as many European countries  to support a large an significant dissemination (se map hereafter to present the ERCIM members in Europe).

# 2.4 Publications

Several publications were made to promote the project within the European and international scientific DL research communities. Among those publications, the ERCIM news magazines offer a valuable opportunity to disseminate information to the targeted scientific communities.

Advertising through ERCIM news (8000 copies) or through other specialised bulletins provides an excellent vector for dissemination.  ERCIM News reports on joint actions of the ERCIM partners, and aims to reflect the contribution made by ERCIM to the European Community in Information Technology.

Through short articles and news items, it provides a forum for the exchange of information between the institutes and also with the wider scientific community. ERCIM News is published quarterly. The printed edition has a circulation of over 7000 copies.

Cyclades was mentioned in ERCIM news in a dedicated article written by Donatella Castelli, “Scholnet and Cyclades: two new digital Library projects”, ERCIM News, April 2000.

Other publications were also enlisted:

- An early version of the questionnaire devised for the requirements collection was communicated to the Open Archives Initiative working group who provided input that helped shape the questionnaire’s final version.

- Donatella Castelli, Pasquale Pagano and Umberto Straccia, Scholnet and Cyclades: extending the role of digital libraries D-Lib Magazine, May 2001

- Finally, a specific Cyclades leaflet has been designed and edited as a handout to support the promotion of the project in various conferences

- Tom Gross from FhG-IPSI produced  “Sharing and Exchanging Knowledge in Communities: The CYCLADES Open Collaborative Virtual Archive Environment.” This paper was presented at Workshop on Community Knowledge at the Seventh European Conference on Computer-Supported Cooperative Work - ECSCW 2001 (Sept. 16, Bonn, Germany). Nakata, K. and Kuutti, K., eds. 2001. pp. 17-24.

# ACTIVITIES AND ACHIEVEMENTS

# 3.1 ERCIM

Activities & Achievements

ERCIM has been paying special attention to starting the project on optimal grounds. The partners were provided with various tools to help them in carrying out their tasks throughout the project. The tools rank from guidelines for writing reports and deliverables to the BSCW workspace on the internet.

The next important move was to prepare an efficient Kick Off meeting. From ERCIM’s experience in other projects some partners sometimes left this meeting with no clearly defined tasks with less accurate deadlines. In Cyclades, the management made strict recommendations to the partners and by the end of the kick-off meeting, all partners had actions to fulfil within a short deadline. By getting the team to work rapidly and, most importantly, jointly on the project, the management has been able to trigger extensive collaboration among partners while giving the whole project the impulse to solve the pending issues rapidly: definition of the expected output, user requirements, interaction between the work-packages, information flow in the consortium, etc…

Having focused on improving the communication flow, ERCIM has also improved the self-assessment of the Project.  The various documents due to the Commission are presented to all partner on the BSCW site for reviewing. Any document can be read, opened or modified. Once all the relevant modifications have been done, the BSCW keeps track of all actions for every document. If a Deliverable has been read by a partner, the BSCW platform can provide the name of the Partners, the date at which he read the document and if any modifications were made.

This is all the more useful as some partners are still not familiar with the Commission documents.

Regarding WP9, ERCIM has brought an additional degree of quality in the work achieved through the evaluation and review of all the strategic documents. Some of these document being necessary for some partners to move onwards in the project, it was WP9’s priority to ensure that such documents fulfilled their role, especially internal roadmap documents that are the cornerstones to the project. ERCIM, along with CNR, has been paying particular attention to improving the self-assessment of the Project. The various documents due to the Commission are presented to all partners on the BSCW site for reviewing. Any document can be read, opened or modified. The final version of the documents and reports are then available of the ANFAS web site, under the document repository section.

In that perspective, the quality of each document produced was reviewed not only by the work-package leaders and the co-ordinator, but also by the person using this document. If it was not regarded as satisfactory, the document was sent back to its author, precising what elements needed further details.

This system, operational from the beginning of the project, was applied to all documents, especially to Deliverable that needed to be reviewed and assessed by all key players of the project before being sent to the European Commission.

Regarding the coordination of the work performed by the Cyclades consortium, ERCIM has brought  and additional degree of quality in the work achieved through the evaluation and review of all the strategic documents. Some of these document being necessary for some partners to move onwards in the project, it was the coordinator’s priority to ensure that such document fulfilled their role, especially internal roadmap documents that are the cornerstones of the project.

In that perspective, the quality of each document produced was reviewed not only by the workpackage leaders and the Scientific Co-ordinator, but also by the person using this document as an input. If it was not regarded as satisfactory, the document was sent back to its author, precising which elements needed further details.  Additional proof-reading was finally done to give the reports its ultimate polish.

This system, operational from the beginning of the project, was applied to all documents, especially to Deliverable that needed to be reviewed and assessed by all key players of the project before being sent to the European Commission.

The collection of every partners’ contribution to the Progress Reports and Man-month effort tables was another co-ordination task carried out. These tables have also been revised and modified in accordance with European Commission’s recommendations (improved tables and graphics) for a better readibility. The Management integrated these elements to realise the documents to be sent to the Commission, only after a  general partners’ assessment of the reports. The Management was also gathering the various detailed Cost Summary  to hand in the  Cost Statement consolidated figures.

Additional efforts  were made by the Management to strengthen the links with other digital Library oriented projects (DELOS (IST-1999-12262),  SCHOLNET (IST-1999-20664),…)  with the aim to foster pragmatic project clustering

In addition, the Technical Coordination followed closely the achievements of each WP individually and brought every partner to further interact with the different WP leaders accordingly to the work programme. Beyond this issue, since all Deliverables and  Reports achieved were reviewed by the partners, they were also required to provide information and feedback to the project management. The outcome here being to define more precisely the general course of action for Cyclades.

Regular technical meetings were also organised to ensure closer collaborative work among the different Cyclades teams involved in the project.  In this perspective also, a preparatory meeting will be organised in Luxembourg on the  20th of January 2002. This will be a rehearsal to the project’s first review and the opportunity for all partners to co-ordinate their actions for new rest of the project.

Regarding the Dissemination activities and achievements of WP7, particular efforts have been made to keep the Cyclades web site regularly updated. While the BSCW co-operative work platform hosted the deliverables and reports “in progress”, the Cyclades web site document repository with restricted access hosted the final and validated version of the documents, similar to those sent to the European Commission.

As for the visibility of the project itself, the web site was totally redesigned to a more professional  and modern style. The logo was not abandoned in order  for the project to keep  its “identification mark” but the fact sheet was redesigned also to match the web site general layout.

Regular information about the project was also given through a specific Digital Library Double page in the ERCIM News magazine , more than 7000 copies of which are distributed every 2 months.

Finally, all the Cyclades partners have been oriented towards increasing their participation to Conferences, workshops and to increase Cyclades related publications to foster the project visibility world-wide, bearing in mind to reach also the potential end-users: archives, libraries,

#### CNR

CNR is actively involved in all the Workpackages, with particular attention to WP 3, 7 and 8.

The CNR team has been ensuring the scientific management of the entire project and has been led to take some strategic decisions. The consortium agreed on some basic issues on the software to be developed within CYCLADES. Indeed, we agreed that all software should rely on open source or freely available software, that is no paid software should be included in CYCLADES. Main programming languages will be Perl and Java. Concerning the background components provided by partners, they will be made available to all the partners for free.

CNR has also contributed to the definition of the Global System Architecture (Deliverable D2.2.1).

During the last six months the CNR has been proceeding with the work involved in developing the Collection Service and Filtering and Recommendation Service for the CYCLADES system prototype (WP3). CNR has also proceeded with coordination of the activities between CYCLADES and OAI (WP8), as well as the overall scientific management of the project. These activities are described below.

# WP3

CNR is responsible WP3 as a whole. Additionally CNR is responsible for the Collection Service (Task 3.3) and Filtering and Recommendation Service (Task 3.4, 3.5) of the CYCLADES system prototype. This phase concentrated on development of the detailed software specifications.

Actions taken during this reporting period:

Collection Service

- Development environment and base technology installed:
- Apache XML-RPC (http://xml.apache.org/xmlrpc), MySQL database, Java

- Concept for database scheme developed

- Some methods implemented
- (addCollection, listCollection)

##### Filtering and Recommendation Service

- Development environment and base technology installed (XML-RPC API, Java, BerkleyDB

- Concept for database scheme developed

- Filtering algorithms defined

- Filtering algorithms implementation in progress

- Recommendation algorithms defined

CNR also contributes significantly to the definition of the Detailed System Specifrication (Deliverable D3.0.1).

# WP8

#### The goals of WP8  are to Monitor progress achieved by CYCLADES and OAI. This monitoring should guarantee that:

- the interoperability agreements defined by OAI and their evolution is correctly understood and used by CYCLADES,

- the impact on the service level of new OAI specs is thoroughly evaluated and feedback is sent to the originators of the changes.

- Feedback to the OAI. This entails that validation and experimentation results will be made available to OAI for undertaking the necessary corrective actions

Meetings with OAi representatives. Regular meetings will be organised throughout the rest of the project to ensure a continuous monitoring.

Actions taken during this reporting period:

Monitoring progress achieved by CYCLADES and OAI.

- Continuous monitoring activity of the OAI (meetings and related papers) is in progress.

- The list of registered repositories as well as the register OAI services is continuously monitored.

Feedback to the OAI.

A first metadata gathering activity has been started:

- Some statistics about the to be gathered data from the OAi compliant archives has been collected.

- Some non-uniformity of the data has been detected.

- The report of this gathering process has been submitted to a OAI Workshop.

- The gathered data seems already to be enough for making the system appealing.

Meetings with OAI representatives

- CYCLADES will collaborate with the OAF (European Open Archive Forum) project, where IEI-CNR is a participant.

##### WP 9

The CNR team has been ensuring the scientific management of the entire project. During the last six months CNR monitored particularly the timing and scientific progress of WP3 (and promoted a technical meeting in Bonn), as well as  the preparation of the first CYCLADES review meeting.

# 3.3 FORTH

Activities & Achievements

The initial objective of Workpackage 1 was to identify relevant user communities, select a user requirements collection and analysis methodology and collect and analyse user requirements regarding the CYCLADES environment.

The first task was the identification of relevant user communities. The following scholarly communities were identified as such :

- the German Society of Physics

- the German Society of Mathematics

- the Italian Society of Mathematics

- the Delos Network of Excellence in Digital Libraries

- the PLANET Network of Excellence in Artificial Intelligence Planning

- the Open Archives Initiative group

Academic and research groups among the partners’ institutions have also been consulted.

The next step consisted in creating the specific questionnaire for eliciting requirements from prospective users of a collaborative archive environment. All partners contributed to the formation of the questionnaire by specifying appropriate questions for the different functional modules of the CYCLADES environment. A goal-directed approach was followed in devising the questionnaire.

Considering the different disciplines of the user groups we intended to address with our questionnaire, an abstraction of technical details was made in order to produce a set of questions that sufficiently covered the entire system functionality, but which were presented in understandable terms by the scientific community at large.  The questionnaire comprises a total of 34 questions distributed as evenly as possible among the different services. A particular effort was made to keep the questionnaire as succinct as possible.

The questionnaire also included a concise description of the CYCLADES objectives and of its different service components. Several versions of the questionnaire were produced, refined as well as modified by the CYCLADES partners. As mentioned above, the questionnaire was also disseminated to the Open Archives Initiative group, whose valuable feedback was accommodated in the final version of the questionnaire. The final version of the questionnaire was included in Appendix A of Deliverable D1.1 (User Requirements Report).

It was decided to electronically disseminate the questionnaire in order to avoid delays with mailing printed versions. The questionnaire was made accessible via the World-Wide Web on a site hosted by ICS-FORTH.

(URL: http://sappho.ics.forth.gr:5000/User_requirements/questionnaire.html).

Solicitation letters were sent by the partners to the above mentioned communities. A total of  34 answers to the questionnaire were collected through the web site. The analysis of the results was presented in  Deliverable D1.1 (User Requirements Report).  The complete set of answers and related statistics were included in Appendix B of the deliverable.

The resulting requirements were used as input in Workpackage 2 for devising detailed functional specifications of the system while taking into account user needs.

The consortium agreed to give a short extension to the period initially assigned for the collection of responses to the questionnaire so that the number of responses could be increased. This extension did not result in any delays for the Workpackage completion.

Within WP2, FORTH undertook the task of specifying the Mediator Service component of Cyclades, following the agreed upon methodology. The task of this component is the provision of a homogeneous interface to the provided services and the integration and dispatching of services within Cyclades. FORTH proposed an extensible architecture for the Mediator component and a simple interservice communication protocol.

Next, from the reporting period, August 2001 to January 2002, ICS-FORTH undertook the task of providing a detailed specification of the Mediator Service of the CYCLADES system prototype. The Mediator Service is the service of the CYCLADES system that integrates all participating services and enables the communication among them. It also supports the global system user interface and controls the registration of users and new services to the system.

More specifically, ICS-FORTH specified and produced a first implementation of the classes and methods that constitute the Mediator Service and which support the addition, removal or update of services, service discovery primitives, error logging and reporting, addition of users, user information logging, access rights management and inter-service communication primitives. A database storing service and user information has been designed and implemented in the Oracle8i relational database management system. The database maintains information about the registered users of the systems and their profiles. Communication of the Mediator Service and the database is implemented through JDBC.

The design and implementation of the Mediator service treats all system components homogeneously. The current implementation renders the system open and extensible, i.e., more services or service instances can be added at any time. The implementation has been carried out in Java using servlet technology and is portable to different platforms.

ICS-FORTH also participated in the detailed specification of the communication protocol for the system services. Specifically, the encoding of the service input/output parameters into the chosen communication protocol (XML-RPC) has been carried out in collaboration with GMD. This task also included the mapping of XML-RPC data types to the respective data types of the Java language as well as, the specification of the unified fault codes to be used in the entire system. A comparison of XML-RPC to SOAP – an XML-based generic communication protocol – was carried out to in order to validate the choice of XML-RPC as the protocol to be used within CYCLADES.

Dimitris Plexousakis and Nick Papadopoulos of ICS-FORTH participated in the meeting that took place in Bonn in December 2001.

Dimitris Plexousakis attended the VLDB 2001 conference in Rome, Italy in September 2001. Services over distributed environments such as the one of CYCLADES are an emerging topic in this major forum of database research. The works reported in this forum are useful in assessing the design and architectural choices made so far in the progress of the project and in understanding the state-of-the art in distributed service environments,

3.4	Fraunhofer FIT

Activities

Fraunhofer FIT is the leader of Workpackage 4, starting at t+19. As this acitvitiy has not started yet, most of the effort of Fraunhofer FIT has however been put into Workpackage 3.

Detailed system specifications were written for the Collaborative Work Service (CWS) and the Rating Management Service (RMS). They contain detailed information on the functionality, the process flow, the internal architecture, the data and methods involved, the user interface, and the interaction with other services for both services.

In preparation of the implementation of the CWS and the RMS the base technologies have been installed and tested: a XML-RPC server using F. Lundhs xmlrpclib from Secret Labs AB; a BSCW server from OrbiTeam; an Apache Web server; a MySQL database; etc. ..

Concerning the CWS the classes for private, project, and community folders, for records and queries, for users, communities, and collections were modelled and partly implemented. The user interface was designed and partly implemented. Concerning the RMS the database scheme for the ratings was developed and implemented. Some methods of the RMS have been made available for the other CYCLADES partners, so they can try out parts of the functionality in real-time (cf. http://CYCLADES.gmd.de/cgi-bin/cyc_cws.cyc).

Fraunhofer FIT has organised a meeting of the CYCLADES partners in St. Augustin on 29-30 November, where the communication protocol, the APIs of the individual services, and the parameter encoding and error codes were discussed. Fraunhofer FIT has then written the precise specification of the communication protocol  in XML-RPC and the parameter encoding including data types, object IDs, and the mapping of XML-RPC data types to the programming languages mainly used in CYCLADES (Java and Python).

Fraunhofer FIT has participated in a workshop on Community Knowledge at the Seventh European Conference on Computer-Supported Cooperative Work - ECSCW 2001 in Bonn.

Achievements:

# User requirements

Analysis of user requirements by means of a Web-based questionnaire; in particular, the feedback of future users brought insight concerning the recommendation service, the rating service, and the collaborative work service

# Shared glossary

Elaboration of a common terminology in the form of a shared glossary for the CYCLADES project

# Specification

Thorough discussion and specification of the system functionality; in particular, the functionality that will be provided by the rating management service and the collaborative work service concerning single-user activities (e.g., registering to the system, logging in, managing private folders and documents) and community activities (e.g., setting up a community, joining and leaving a community, awareness of the activities of the other community members, and communication with other community members). For these parts of system use cases were developed and activity diagrams were drawn. The overall architecture of the CYCLADES system was specified and the communication between the rating management service and the collaborative work service on the one hand and the other services on the other hand was clarified and documented by means of interaction diagrams.

But beyond  this technical contribution to the project, GMD has offered a strong support to the dissemination activities  by producing  a specific leaflet in English and German for distribution at conferences as well as to visitors at GMD-FIT.

This institute  is also promoting the project through the information found under the CYCLADES project  GMD page linked to ERCIM (cf. http://fit.gmd.de/projects/cyclades )

GMD has also been active in its participation to a panel on ‘e-Democracy: A Panacea or Pandora’s Box?’ at the 14th Bled Electronic Commerce Conference25-26/6/01. The leaflet produced were distributed and a specific target audience was successfully  reached during this conference.

3.5      UNIDO

Activities and Achievements:

For work package WP2, the functionality of the proposed system was specified in more detail, taking into account the user requirements resulting from WP1.

Different user roles were identified and described, and for each role, the use cases were discussed in detail. Each partner developed activity diagrams to describe the user’s interaction with the system. The use cases and diagrams will later form the basis for testing the functionality of the implemented system.

Based on the proposed behaviour of the system from the user perspective, the corresponding necessary system activity was identified. The resulting system actions were assigned to system components that will be implemented by the Cyclades services, and the most relevant classes were defined.

Then, the interaction between the resulting classes and services was specified in detail, also defining the necessary methods that will be called during service interaction. For each activity diagram, corresponding interaction diagrams were drawn. Thus, it was verified that the class definitions contain all the methods that have to be known between services in order to implement the functionality defined by the use cases and background activity descriptions.

The services thus identified are:

- Access Service

This service will provide harvest-based gathering of metadata from different open archives, the possibility to register and unregister archives, and a basic search functionality (for internal use only).

- Collaborative Work Service

This service will implement a folder environment for the user to store, organise, rate, annotate and share metadata records and documents with her project partners and within a community.

- Search and Browse Service

This service will provide a sophisticated environment for searching and browsing in virtual collections of metadata records.

- Collection Service

The management of virtual collections of metadata records will be the purpose of this service.

- Filtering and Recommendation Service

This service will provide personalised filtering both for queries and for query results, and recommendation of records, users, communities and collections to the user.

- Mediator Service

The task of this service will be to provide a homogeneous outward appearance for the system, to integrate the other services, including any future service types yet to be defined, and to provide security.

For inter-service communication, different protocols were discussed. XMP-RPC was chosen, as it is already well established and tested. The communication will be implemented in a separate layer so that it might be changed in the future to some other protocol.

The suitability of various existing software tools as building blocks for the Cyclades system was discussed. BSCW will be adapted to function as Collaborative Work Service.

The GUI of the future system will consist of a graphical user interface for every service that has interaction with the user, and a general system GUI that will call and integrate the graphical user interfaces of the individual services.

The proposed core services of the Cyclades system are designed to run autonomously and work together via the Mediator service which will function as a registry. Replication is provided for in the current design, while distribution of services will not be supported yet. The possibility of service distribution was discussed at length, however, to make sure that the current design will be easily extendable to support distribution of services in the future.

During the second half of the year, UniDo has been working on Dortmund’s contributions to WP3.

As the Cyclades system will harvest metadata from electronic sources that adhere to the Open Archives specification, and will furthermore provide value-added services on top of this metadata, the Cyclades system can be seen as an Open Archives service provider. UniDo, as the Cyclades partner who is developing the harvesting component, is interested in keeping close contact with the Open Archives community.

For the services to be developed at Dortmund, a database system and programming tools were chosen, installed, and tested. UniDo will use Perl, Java, and Tomcat for the prototype development. The database system chosen for the Access Service prototype is Postgres, but the internal architecture of the service has been designed in such a way that Postgres be easily substituted by other relational database systems.

An abstract syntax both for the formulation of queries, and for the definition of collection filtering conditions was defined, allowing mandatory as well as optional, weighted query conditions.

The internal architecture of the Access Service and the Search and Browse Service was specified. An important design consideration was modularity, so that individual components can be easily adapted or substituted later.

The first component of the Access Service, the harvesting and indexing component, has been implemented. UniDo is currently running the component in a test environment.

One problem that UniDo came upon during the first test harvestings is the internal heterogeneity of the metadata provided by the different archives. The Open Archives protocol specifies a uniform way of accessing the data, and one common format for metadata records as minimum, but it does not further define the content of the fields inside the metadata records. This leads to very heterogeneous data which results in difficult indexing and retrieval. UniDo has made several suggestions to alleviate this problem and presented them in a short paper at the ECDL 2001 Workshop On Experimental OAI Based Digital Library Systems in September 2001 in Darmstadt.

# OTHER

- GMD is merging with FRAUNHOFER and has officially changed its name

- Within UNIDO, Sascha Kriewel was hired as a research assistant in July 2001 to reinforce the Cyclades team.

- DEVIATION FROM PLAN

None.